## Slide 1: Home and Community Based Services Settings Rule Corrective Action Plan Next Steps
May 31, 2023

## Slide 2: GOALS OF PRESENTATION
Overview of HCBS Settings Rule
CMS feedback from the Site Reviews from other States
Corrective Action Plan Discussion
Ongoing Compliance with HCBS
Next Steps

## Slide 3: HCBS SETTINGS RULE OVERVIEW

## Slide 4: Home and Community-Based Services Settings Rule Timeline
March 17, 2014 – Centers for Medicare and Medicaid Services issued the HCBS Settings Final rule AND gave all states 5 years, 3/17/2019, to come into compliance.
2014-2015- Louisiana reviewed and assessed our waiver rules, manuals, processes and did initial assessments of settings to determine where we stood with the HCBS Settings Rule
3/17/2015- Louisiana submitted our Statewide Transition Plan
2015-2017-Louisiana began working towards compliance:
  Asked Nonresidential and Residential Providers to complete self-assessments
  LGEs/OCDD completed desk audits of a 20% sample of residential and nonresidential providers
  SCs completed initial individual surveys with all individuals
  LGE/OCDD completed onsite assessments with ALL nonresidential providers
  Providers who were determined to not be in compliance with the HCBS Settings Rule had to complete a Transition Plan to explain the measures they would take to meet compliance
  March 3, 2017- Louisiana received Initial Approval on the STP

## Slide 5: Home and Community-Based Services Settings Rule Timeline
  2017-2019:
    LGE/OCDD worked with nonresidential providers on their Transition Plans, provided training, onsite TA visits in order to assist providers in moving towards compliance
  May 9, 2017, CMS changed the final compliance date to March 17, 2022.
  July 1, 2019-OCDD joined the State Employment Leadership Network
  March 17, 2020- New date for compliance with the HCBS Settings Rule
  2020-2021:
    Nonresidential providers were shutdown by the Public Health Officer (PHO) due to Covid-19 for months
    Individuals were able to convert day program hours to in-home hours under an Appendix K flexibility
    Nonresidential providers were allowed to reopen under guidance and precautions as outlined by the PHO
    PHO lifted the restrictions
    July 14, 2020, CMS pushed the final date of compliance to March 17, 2023.
  2021-2022:
    Nonresidential providers continued to reopen and work towards compliance with the HCBS Settings Rule
    ALL individuals who reside in a Provider Owned or Controlled Residential Setting received an initial onsite visit
    October 4, 2022- Louisiana received Final Approval on the STP
    Some Nonresidential providers were checked as being in compliance
    Individuals continued to be allowed to convert day program hours to in-home hours
    CMS allowed states to request a Corrective Action Plan (CAP) if circumstances keeping them from meeting compliance were related to the Public Health Emergency (PHE)
    December 1, 2022- OCDD requested a CAP. The CAP applies only to settings that were eligible for the transition period (setting types in the state’s HCBS delivery system as of the effective date of the final rule). Any NEW settings must come into the system compliant

## Slide 6: Home and Community-Based Services Settings Rule Timeline
  2023:
    CMS provided feedback on the Site Visits from states regarding issues they found related to compliance with the HCBS Settings Rule
    March 17, 2023- Final date for Compliance with the HCBS Settings Rule (Louisiana is under a CAP), since the LA STP is no longer in effect, except for the ongoing monitoring.
    OCDD visited various nonresidential programs around the state during the PHE Roadshow
    May 11, 2023- PHE ENDS
    May 24, 2023- CAP received final approval.
    November 11, 2023- PHE flexibilities end. i.e. conversion of nonresidential program hours ends

## Slide 7: Intent of the Final Rule
The setting in which the person receives services “is integrated in and supports full access of individuals receiving Medicaid HCBS to the greater community, including opportunities to seek employment and work in competitive integrated settings, engage in community life, control personal resources, and receive services in the community, to the same degree of access as individuals not receiving Medicaid HCBS.”

## Slide 8: Settings that are NOT Home and Community-Based
Nursing facility
Institution for mental diseases (IMD)
Intermediate care facility for individuals with intellectual disabilities (ICF/IID)
Hospital

## Slide 9: Settings PRESUMED NOT to Be Home and Community-Based
Heightened Scrutiny
Settings in a publicly or privately-owned facility providing inpatient treatment
Settings on grounds of, or adjacent to, a public institution
Settings with the effect of isolating individuals from the broader community of individuals not receiving Medicaid HCBS

## Slide 10: Settings PRESUMED NOT to Be Home and Community-Based Settings
Heightened Scrutiny
These settings may NOT be included in states’ HCBS waiver programs unless:
A state submits evidence (including public comment) demonstrating that the setting does have the qualities of a Home and Community-Based Setting and NOT the qualities of an institution

## Slide 11: Home and Community Based Setting Requirements
The Home and Community Based Setting must demonstrate the following qualities! (42 CFR §441.301(c)(4)(i) )
Is integrated in and supports access to the greater community
Provides opportunities to seek employment and work in competitive integrated settings, engage in community life, and control personal resources
Ensures the individual receives services in the community to the same degree of access as individuals not receiving Medicaid home and community-based services
Notes: FIRST REQUIREMENT ON THE CAP-

## Slide 12: Home and Community Based Setting Requirements
The Home and Community Based Setting must demonstrate the following quality! (42 CFR §441.301(c)(4)(ii))
Is selected by the individual from among setting options, including non-disability specific settings and an option for a private unit in a residential setting
    Person-centered service plans document the options based on the individual’s needs, preferences, and for residential settings, the individual’s resources
Notes: 2ND CAP

## Slide 13: HOME AND COMMUNITY BASED SETTING REQUIREMENTS
The Home and Community Based Setting must demonstrate the following qualities! (42 §CFR 441.301(c)(4)(iv))
Ensures an individual’s rights of privacy, dignity, respect, and freedom from coercion and restraint
Optimizes individual initiative, autonomy, and independence in making life choices
Notes: 3rd CAP REQUIREMENT

## Slide 14: HOME AND COMMUNITY BASED SETTING REQUIREMENTS
The Home and Community Based Setting must demonstrate the following quality! (42 §CFR 441.301(c)(4)(v))
Facilitates individual choice regarding services and supports, and who provides them
Notes: AND 4TH REQUIREMENT
Individuals must have the opportunity for “informed choice” during the person-centered planning process.
Options must include “non-disability specific settings”
A person-centered approach to informed choice is to always presume competence.
CMS also reminds states that informed choice is a critical component of the person-centered planning process:
  Use appropriate modes of communication to give people information they need to exercise informed choice and assist them in doing so;
  Provide or assist people in acquiring information that enables them to exercise informed choice in the development of their person-centered service plans; and
  Develop and implement flexible policies that allow people the opportunity to make meaningful choices

## Slide 15: HOME AND COMMUNITY BASED SETTING REQUIREMENTS
PERSON-CENTERED PLAN OF CARE
Final rule included changes to the requirements regarding person-centered service plans for HCBS waivers:
The person-centered service plan must be developed through a person-centered planning process and documents choice and options and how those choices are provided.
Plans must:
Reflect services/supports that are important for the individual to meet the needs identified through the functional needs assessment;
Reflect services/supports that are important to the individual; and
Reflect that the setting has been chosen by the individual.
Be finalized and agreed to, with the informed consent of the individual in writing, and signed by all individuals and providers responsible for its implementation.
Be distributed to the individual and other people involved in the plan.
Notes: Msut be in compliance

## Slide 16: PERSON-CENTERED POC AND THE ROLE OF THE SUPPORT COORDINATOR
Support Coordinator:
  Works with the individual to determine who should be involved, convenes the team and (to the extent the individual wishes) assists the participant in leading the team.
  Offers choices in services and supports based on each person's PCP, including choices about what is important to the person with regard to services and supports.
  Provides alternatives to facilitate each person's access to services or activities in the community as desired, including access to employment, transportation and flexible schedules.
  Is attuned to each individual’s desire for new services or settings and arranges for the services to take place.
  Monitors the service plan to ensure services are provided and adjusts accordingly

## Slide 17: PERSON-CENTERED POC AND THE ROLE OF PROVIDERS
Provider:
Ensure that the POC is implemented or reflected in how each person is served in that setting.
Offer services and supports based on each person’s POC, including choices about what is important to the person with regard to services and supports.
Provide alternatives or work to facilitate each person’s access to services or activities in the community as desired, including access to transportation and flexible schedules.
Be attuned to each person’s desire for new services or settings and refer them to their support coordinator for assistance in updating their POC.

## Slide 18: Informed Choice
Individuals must have the opportunity for “informed choice” during the person-centered planning process.
Options must include “non-disability specific settings”
A person-centered approach to informed choice is to always presume competence.
CMS also reminds states that informed choice is a critical component of the person-centered planning process:
  Use appropriate modes of communication to give people information they need to exercise informed choice and assist them in doing so;
  Provide or assist people in acquiring information that enables them to exercise informed choice in the development of their person-centered service plans; and
  Develop and implement flexible policies that allow people the opportunity to make meaningful choices.

## Slide 19: HOME AND COMMUNITY BASED SETTING REQUIREMENTS
OPPORTUNITY TO CONTROL PERSONAL RESOURCES
Individuals must be offered the opportunity to “control personal resources”.
  Counseling may be needed in regards to financial competency
  Work with the individual where they are and what’s important to the person
  Set goals with the person for where they are
  Should have access to their funds and shouldn’t have to wait or go through a lengthy process to obtain funds
Notes: Must be in compliance

## Slide 20: HOME AND COMMUNITY BASED SETTING REQUIREMENTS
FULL ACCESS TO COMPETITIVE INTEGRATED EMPLOYMENT
Person is not required to seek individual employment, but cannot waive the opportunity to seek employment indefinitely.
  Should be at least an annual discussion about individual employment
  Goals should be included if the individual is interested in working at any point
  Group Employment should not be the final goal for everyone
  No sheltered workshop is allowed
  No subminimum wage

## Slide 21: REGULATORY REQUIREMENTS THAT MUST ALREADY BE IN COMPLIANCE
Utilizing the Person Centered Planning Process
Ensuring an individual’s rights of privacy, dignity, respect, and freedom from coercion and restraint
Optimizing individual initiative, autonomy, and independence in making life choices
Facilitating individual choice regarding services and supports, and who provides them
Ensuring an individual has the opportunity to control personal resources

## Slide 22: REGULATORY REQUIREMENTS SUBJECT TO THE CAP
All settings:
The setting is integrated in and supports full access of individuals receiving Medicaid HCBS to the greater community, including opportunities to seek employment and work in competitive integrated settings, engage in community life, and receive services in the community, to the same degree of access as individuals not receiving Medicaid HCBS at 42 CFR §441.301(c)(4)(i) (entire criterion except for “control personal resources”),
The setting is selected by the individual from among setting options including non-disability specific settings and an option for a private unit in a residential setting. The setting options are identified and documented in the person-centered service plan and are based on the individual’s needs, preferences, and for residential settings, resources available for room and board at 42 CFR §441.301(c)(4)(ii),
Optimizes, but does not regiment, individual initiative, autonomy, and independence in making life choices, including but not limited to, daily activities, physical environment, and with whom to interact at 42 §CFR 441.301(c)(4)(iv), and
Facilitates individual choice regarding services and supports, and who provides them at 42 §CFR 441.301(c)(4)(v).
Provider-owned or controlled residential settings:
Individuals sharing units have a choice of roommate in that setting at 42 CFR §441.301(c)(4)(vi)(B)(2), and
Individuals have the freedom and support to control their own schedules and activities at 42 CFR §441.301(c)(4)(vi)(C) (entire criterion except for “have access to food at any time”).

## Slide 23: CMS FEEDBACK FROM SITE VISITS

## Slide 24: INSIGHTS FROM CMS’ SITE VISITS
In calendar years 2022-2023, approximately 14 states have received, or will receive, a site visit from CMS.
CMS selected states based on presumptively institutional settings that were submitted or settings in the state that were identified by federal partners or stakeholders.

## Slide 25: CMS ONSITE VISITS
The CMS Review Team typically receives a tour of the setting, reviews POCs and other documents on site, and speaks with HCBS participants and direct support professionals (DSPs).
Following the visit, CMS provides the state with a debrief call and follows up with a written site visit report that contains the findings and potential remediation strategies. The report also acknowledges promising practices.

## Slide 26: CMS REPORTED TRENDS REGARDING PERSON CENTERED PLANS
CMS findings:
  Settings do not typically have the current POC for all Medicaid HCBS beneficiaries who are served at the setting;
  Individuals do not appear to have participated in the plan development and/or have not signed the plan; and
  Individuals are functioning under provider-specific plans of care, or in some cases there are plans only known to the support coordinator and the individual.
  POC often did not record what was important to people, their preferences or their goals.
  There was often no indication in the plans that choice had been offered, whether it was choice of setting, living location, employment or community integration or how the person managed their personal resources.
  Restrictions were observed that were not supported by a specific assessed need for the individual or justified in the individual’s person-centered plan and, therefore, are not permissible under the regulations as an individual modification to the regulatory criteria.
Notes: DOCUMENTATION

## Slide 27: CMS REPORTED TRENDS ON PROVIDER STAFF TRAINING ON HCBS
CMS Findings:
Staff and administration were not aware of the HCBS settings requirements; and
When asked to describe the difference between institutional settings, and HCBS settings, and whether there was specific training for HCBS, staff frequently provided responses about the level of support that people need rather than responses related to community integration.
Notes: ADD TRAININGS ON HCBS AND PEOPLE FIRST LANGUAGE

## Slide 28: CMS REPORTED TRENDS ON COMMUNITY INTEGRATION: LIMITED ACCESS TO SETTINGS
CMS Findings:
Restricted access to buildings due to PHE protocols so that all visitors enter through a single entrance and can be screened prior to entry.
These single points of entry/exit for HCBS settings that are connected to institutional settings are typically located at the entrance to the institutional setting.
(Settings should have a plan to reopen the separate entrances once the PHE protocols are lifted and states should have a plan to verify that this is done.)
PHE ended 5/11/2023

## Slide 29: CMS REPORTED TRENDS ON COMMUNITY INTEGRATION: EMPLOYMENT AND ACTIVITIES
CMS Findings:
Providers will reference ‘group activities’ that take place off-site as “community” activities even when individuals are not integrated with the broader community.
Employment:
  Some settings, staff or individuals have described being “on the job” or “at work” when they are actually referring to attendance at day programs.
  Some participants expressed the desire to work, but there was nothing related to employment services in their POC.
Community Activities:
  Some settings defined full community integration as activities that occur on the provider’s campus, and attendance at a campus/provider function (dance, party, holiday event, etc.) that is only for individuals with disabilities who reside or attend the provider agency’s programs.
  Community engagement was often described as group trips and activities rather than individualized opportunities for meaningful engagement in community life, or activities that are only inclusive of people with disabilities.
  Community activities that are ‘in the community’ but still only people with disabilities are included
Reverse integration is not the same as community integration.
  Having the community ‘come in’ to the building is okay but is NOT Community Integration- it might be considered part and help to facilitate community integration but by itself does not meet the definition of community integration.
Notes: Separate book clubs at the library
Separate movie day
Separate dance at the community center
These are not examples of ‘community activities’

## Slide 30: RESIDENTIAL PROVIDER OWNED/CONTROLLED SETTINGS
The unit or dwelling is a specific physical place that can be owned, rented, or occupied under a legally enforceable agreement by the individual receiving services, and the individual has, at a minimum, the same responsibilities and protections from eviction that tenants have under the landlord/tenant law of the State, county, city, or other designated entity.
Notes: RESIDENTIAL

## Slide 31: CMS REPORTED TRENDS REGARDING PROVIDER OWNED/CONTROLLED SETTINGS
CMS Findings:
States not identifying provider-owned or controlled settings as such if the setting is not formally owned by a provider of HCBS.
CMS reminds states and stakeholders that the additional regulatory criteria found at 42 CFR §441.301(c)(vi) also applies to settings controlled by a service provider.
  This includes scenarios in which a provider has influence over whether an individual is accepted for residency.
  This includes scenarios in which the landlord has influence over which service providers the individual in the setting uses.
Notes: RESIDENTIAL

## Slide 32: CMS REPORTED TRENDS REGARDING PROVIDER OWNED/CONTROLLED SETTINGS
CMS Findings:
  Access to visitors was restricted;
  Community integration is limited;
  Lack of Provider staff training on HCBS; and
  Lease or residency agreement was restricted
    Examples of restrictive language in lease or residency agreements that isn’t typical lease agreements
      Work on the provider’s worksite;
      Pay the provider for lack of attendance at the worksite;
      Move out during specified periods of time; and/or
      Be evicted if the individual’s needs increase even if resources were available to provide additional support
Notes: RESIDENTIAL BUT DOES YOUR AGENCY DO ANY TYPE OF RESTRICTIONS WHETHER WRITTEN ON PRACTICED
POLICY REVIEW
STAFF TRAININGS

## Slide 33: CMS REPORTED TRENDS REGARDING PROVIDER OWNED/CONTROLLED SETTINGS
Examples of restrictions include:
Residential settings that prohibit overnight guests.
Residential settings that set a limit on number of visits an individual can receive.
Residential staff who indicate there is no written agency policy, but staff may prevent a person from having visitors or restrict the time of day the person can have visitors.
Participants in a smaller subset of settings reported the need to get approval to have guests and that having guests was an infrequent experience if they had guests at all.
Notes: RESIDENTIAL

## Slide 34: CMS REPORTED TRENDS IN MODIFICATIONS OF THE ADDITIONAL CONDITIONS/RIGHTS RESTRICTIONS
CMS found restrictions in practice that didn’t adhere to the regulatory requirements:
The restrictions were not supported by a specific assessed need for the individual or justified in the individual’s person-centered plan and, therefore, are not permissible under the regulations as an individual modification to the regulatory criteria.
Restrictions included:
  not having locks on bedroom or bathroom doors,
  restricted access to the community (e.g., locked building entrance doors with no keys or other accommodations afforded to the individual),
  behavior plans requiring individuals to earn activities that are their right or using the loss of activities and rights as a negative consequence, and
  restrictions on visitors, smoking, and access to food
Notes: RESIDENTIAL

## Slide 35: MODIFICATIONS OF THE ADDITIONAL CONDITIONS: REGULATORY REQUIREMENTS
The following modification requirements must be documented in the person-centered POC:
Identify a specific and individualized assessed need.
Document the positive interventions and supports used prior to any modifications to the person-centered service plan.
Document less intrusive methods of meeting the need that have been tried but did not work.
Include a clear description of the condition that is directly proportionate to the specific assessed need.
Include regular collection and review of data to measure the ongoing effectiveness of the modification.
Include established time limits for periodic reviews to determine if the modification is still necessary or can be terminated.
Include the informed consent of the individual.
Include an assurance that interventions and supports will cause no harm to the individual
Notes: RESTRICTIONS MUST BE DOCUMENTED

## Slide 36: PROMISING PRACTICES FOR REMEDIATING SETTINGS
Providers can work to increase engagement with the broader community by:
  Developing partnerships with community-based entities, resulting in inclusion in the broader community;
  Establishing a community-based advisory group;
  Implementing a broad range of services and supports, programming, and multiple daily activities to facilitate access to the broader community that allows for each individual to be able to select from an array of individual and/or group options and control their own schedule.
  Activities should promote skills development and facilitate training and educational opportunities among HCBS beneficiaries designed to attain and expand opportunities for community-based integration. Examples include:
      volunteering,
      social and recreational activities, and
      competitive integrated employment
Notes: INCREASING VOLUNTEERING ACTIVITIES
INCREASING OPPORTUNTIES TO LEARN ABOUT INDIVDIUAL EMPLOYMENT
CREATING A COMMUNITY ENGAGEMENT BOARD TO CREATE MORE OPPORTUNTIES IN THE COMMUNITY AND INCREASE THE COMMUNITY AWARENESS- COULD PARTNER WITH LRS/DOE/LGE/OTHER PROVIDERS AS WELL AS COMMUNITY LEADERS – USE AS A COMMUNITY OF PRACTICE TO ENGAGE MORE IN THE COMMUNITY

## Slide 37: PROMISING PRACTICES FOR REMEDIATING SETTINGS
Expose beneficiaries to community activities and situations comparable to those in which individuals not receiving HCBS routinely engage;
Promote greater HCBS beneficiary independence and autonomy.
Implementing organizational changes that:
  Assure the required level of support, including appropriate staffing, and adequate transportation options to offer more options that facilitate optimal community engagement based on individual preferences (as articulated in the POC/Attachment) and/or
  Decentralize staff structures to promote greater flexibility and encourage staffing focused on individuals’ access to and participation in the broader community rather than centralized insular staff models focused around a specific facility/site.
Notes: GETTING INVOLVED WITH A PEOPLE FIRST GROUP OR SELF ADVOCACY GROUPS
TRAINING STAFF
MORE COMMUNITY ACTIVITIES AND OPTIONS
SMALLER GROUPS AND MORE OPPORTUNTIES TO GO DO THINGS OF INTEREST
EXPLORING

## Slide 38: PROMISING PRACTICES FOR REMEDIATING SETTINGS
Expanding strategies for increasing beneficiary access to transportation, including through existing public transportation, friends/family, and volunteer organizations, to activities in the broader community.
  This could include providing transportation in a way that promotes ease of access and optimizes individuals’ ability to select their own options and make decisions about their services and supports.
Notes: TRANSPORTATION IS ALWAYS A BARRIER= HOW TO WORK THROUGH THIS… ENGAGING LOCAL CHURCHES, VOLUNTEER GROUPS, ETC TO DISCUSS THIS AND WORK THROUGH ISSUES
NOW PAYING MORE FOR TRANSPORATION BUT WHAT ABOUT AFTER THE TYPICAL 8-2 HOURS
We can’t just say that they don’t have transportation and can’t work or go places and then never address it in the POC

## Slide 39: CORRECTIVE ACTION PLAN

## Slide 40: GOAL OF HCBS SETTINGS RULE
The HCBS Settings Rule was created to ensure that every person receiving Medicaid-funded HCBS has full access to the benefits of community living.
It protects individuals’ autonomy to make choices and to control the decisions in their lives, which most people take for granted. This includes controlling personal resources; being treated with privacy, dignity, respect, and freedom from coercion and restraint; deciding what and when to eat; having visitors; being able to lock doors; and having the protections of a lease or other legally enforceable agreement.
The rule requires a person-centered process for receipt of HCBS, which means that the individuals receiving services direct the planning process and the plan reflects their own preferences and goals they have set for themselves.

## Slide 41: CORRECTIVE ACTION PLAN
CMS allowed states to request a Corrective Action Plan for reasons related to the Public Health Emergency.
Louisiana requested a CAP on December 1, 2022 and received final approval on May 24, 2023.
The CAP was requested due to the ‘workforce shortage’ which we believe has not allowed our state to reach full compliance in the staff dependent provisions of the HCBS Settings rule.
  Access to the community in smaller ratios (Community Life Engagement)
  Opportunities for individual employment in the community
  Choices for non-disability specific settings (community options)

## Slide 42: CAP ENFORCEMENT MECHANISMS
The state will report to CMS on progress with activities, milestones, and timeframes outlined in the approved CAP.
Full compliance is achieved when all Medicaid-funded HCBS is rendered in a compliant setting.
Closure of the CAP will be granted after the state completes the activities described in the approved CAP, at which point the state will be in full compliance with all HCBS settings provisions of the regulation.
In the event a state does not comply with or complete its CAP, CMS will use the enforcement flexibilities authorized under Medicaid rules including:
  General Medicaid rules that apply to all authorities related to Federal Financial Participation (FFP) that permit deferrals or disallowances at 42 CFR Part 430 Subpart C; and
  Strategies to ensure compliance under 1915(c) waivers including, but not limited to, enrollment moratoriums at 42 CFR §441.304(g)(3).

## Slide 43: REGULATORY CRITERIA SUBJECT TO THE CAP
All settings:
The setting is integrated in and supports full access of individuals receiving Medicaid HCBS to the greater community, including opportunities to seek employment and work in competitive integrated settings, engage in community life, and receive services in the community, to the same degree of access as individuals not receiving Medicaid HCBS at 42 CFR §441.301(c)(4)(i) (entire criterion except for “control personal resources”),
The setting is selected by the individual from among setting options including non-disability specific settings and an option for a private unit in a residential setting. The setting options are identified and documented in the person-centered service plan and are based on the individual’s needs, preferences, and for residential settings, resources available for room and board at 42 CFR §441.301(c)(4)(ii),
Optimizes, but does not regiment, individual initiative, autonomy, and independence in making life choices, including but not limited to, daily activities, physical environment, and with whom to interact at 42 §CFR 441.301(c)(4)(iv), and
Facilitates individual choice regarding services and supports, and who provides them at 42 §CFR 441.301(c)(4)(v).
Provider-owned or controlled residential settings:
Individuals sharing units have a choice of roommate in that setting at 42 CFR §441.301(c)(4)(vi)(B)(2), and
Individuals have the freedom and support to control their own schedules and activities at 42 CFR §441.301(c)(4)(vi)(C) (entire criterion except for “have access to food at any time”).

## Slide 44: Corrective Action Plan
Issued memo announcing the upcoming training to discuss the Corrective Action Plan. | May 9, 2023 | May 9, 2023
Conduct training and provide direction for submitting a CAP to the settings who are not in compliance. | May 31, 2023 | May 31, 2023
Distribute application, approve CAPs for the settings who are approvable and notify the setting. | June 1, 2023 | July 31, 2023
Notify providers, whose CAP is not approvable, and begin the disenrollment process. | June 1, 2023 | August 30, 2023
Notify the individuals of the setting’s non-compliance and offer Freedom of Choice of settings who have been deemed as compliant with the HCBS Settings Rule. | June 1, 2023 | September 30, 2023
Provide technical guidance, training, and support to settings approved for the CAP extension. Continue monitoring ongoing remediation efforts of the settings. | June 1, 2023 | January 31, 2024
Continue efforts being made to increase workforce through partnerships with community partners. | March 17, 2023 | December 31, 2024
Conduct final onsite validation visits for those settings with an approved CAP but not under heightened scrutiny review. | February 1, 2024 | July 31, 2024
Notify setting of compliance determination and proceed with disenrollment of the setting if failed to remediate the areas of noncompliance. | May 1, 2024 | September 30, 2024
Notify the individuals of setting that failed to remediate and offer Freedom of Choice of settings who have been deemed as compliant with the HCBS Settings Rule. | June 1, 2024 | October 31, 2024
Complete the transition of individuals to a compliant setting. | August 1, 2024 | December 31, 2024
HEIGHTENED SCRUTINY ACTIVITIES | BEGIN DATE | END DATE
Conduct onsite review and complete the Heightened Scrutiny Report that is to be posted for the setting that is serving waiver beneficiaries. | July 1, 2023 | August 1 30, 2023
Post the Heightened Scrutiny Report for public comment for 30 days. | August 1, 2023 | September 30, 2023
Submit information to CMS on presumptively institutional settings selected by CMS for a sampled heightened scrutiny review. | October 1, 2023 | November 30, 2023
Address heightened scrutiny findings related to CMS’ heightened scrutiny review including, as applicable, remediation of all similarly situated settings that utilize a similar service delivery model and, as applicable, any overall assessment processes of all providers of HCBS in the state to ensure that all providers are being assessed appropriately against the regulatory settings criteria. | Date CMS issues findings to the state | 3 months post the date CMS issues and findings to the state
STATEWIDE COMPLIANCE FOR ALL SETTINGS |  | 
Final Compliance statewide with HCBS settings rule. | ---- | The later of 12/31/2024 – or 3 months post the date CMS issues findings to the state for the HS settings

## Slide 45: MILESTONE: PROVIDER CORRECTIVE ACTION PLAN
June 1, 2023- July 31, 2023
Distribute application, approve CAPs for the settings who are approvable and notify the setting.
June 1, 2023-August 30, 2023
Notify providers, whose CAP is not approvable, and begin the disenrollment process.
June 1, 2023-September 30, 2023
Notify the individuals of the setting’s non-compliance and offer Freedom of Choice of settings who have been deemed as compliant with the HCBS Settings Rule.

## Slide 46: MILESTONE: TECHNICAL GUIDANCE AND TRAINING
June 1, 2023-January 31, 2024
Provide technical guidance, training, and support to settings approved for the CAP extension. Continue monitoring ongoing remediation efforts of the settings.

## Slide 47: MILESTONE: FINAL VALIDATION
February 1, 2024-July 31, 2024
Conduct final onsite validation visits for those settings with an approved CAP but not under heightened scrutiny review.

## Slide 48: MILESTONE: DISENROLLMENT
May 1, 2024-September 30, 2024
Notify setting of compliance determination and proceed with disenrollment of the setting if failed to remediate the areas of noncompliance.

## Slide 49: MILESTONE: TRANSITION
June 1, 2024-October 31, 2024
Notify the individuals of setting that failed to remediate and offer Freedom of Choice of settings who have been deemed as compliant with the HCBS Settings Rule.
August 1, 2024-December 31, 2024
Complete the transition of individuals to a compliant setting.

## Slide 50: MILESTONE: HEIGHTENED SCRUTINY
July 1, 2023- August 30, 2023
Conduct onsite review and complete the Heightened Scrutiny Report that is to be posted for the setting that is serving waiver beneficiaries.
August 1, 2023-September 30, 2023
Post the Heightened Scrutiny Report for public comment for 30 days.
October 1, 2023-November 30, 2023
Submit information to CMS on presumptively institutional settings selected by CMS for a sampled heightened scrutiny review.
Date CMS issues findings to the state- 3 months post the date CMS issues and findings to the state
Address heightened scrutiny findings related to CMS’ heightened scrutiny review including, as applicable, remediation of all similarly situated settings that utilize a similar service delivery model and, as applicable, any overall assessment processes of all providers of HCBS in the state to ensure that all providers are being assessed appropriately against the regulatory settings criteria.

## Slide 51: MILESTONE: FINAL COMPLIANCE
12/31/2024 or 3 months post the date CMS issues findings to the state for the Heightened Scrutiny settings
Final Compliance statewide with HCBS settings rule.

## Slide 52: CORRECTIVE ACTION PLAN GUIDELINES
If you believe your agency is in compliance, notify the LGE and someone will visit your agency and review records and your agency for final compliance.
  If at that time, your agency has not met ALL of the requirements for compliance, the disenrollment process will begin
If you believe your agency is NOT in compliance, use the designated ‘CAP Request Form’ and complete the CAP based on the areas that your setting requires additional time to come into compliance.

## Slide 53: CORRECTIVE ACTION PLAN FORM
AGENCY NAME: (please complete a separate form for each location)
CONTACT INFORMATION:
REGION:
NUMBER OF WAIVER PARTICIPANTS FOR EACH SERVICE:
  DAY HABILITATION/COMMUNITY LIFE ENGAGEMENT:
  PREVOCATIONAL/COMMUNITY CAREER PLANNING:
  GROUP SUPPORTED EMPLOYMENT:
  INDIVIDUAL SUPPORTED EMPLOYMENT:
The Corrective Action Plan (CAP) may be requested through January 30, 2024, at which time onsite validation visits will begin. Your agency may choose to not submit a CAP if you believe your agency is in compliance.
Please initial the appropriate choice.
__________ Our Agency has reviewed the HCBS Requirements and we believe we are in compliance and therefore we are requesting to move forward with an onsite validation visit.
__________Our Agency is requesting a CAP in order to have additional time to come into compliance with the HCBS Settings Rule for the following time period:
CAP Begin date: ______________ CAP End date: _________________
Agency Representative Signature _______________________________________ Date ____________________
If your agency is requesting a Corrective Action Plan (CAP), please complete the remainder of the form.

## Slide 54: CORRECTIVE ACTION PLAN FORM
Initial each CAP Expectation below:
___________ Submit monthly reports to the LGE office on the progress made towards each milestone for each requirement our agency is not in compliance.
___________ First report is due on July 31, 2023 and the last day of the month thereafter as long as a CAP is in place.
___________ Request onsite technical guidance and assistance or training as needed.
___________ Provide training to staff on the HCBS Settings Rule and Person Centered Language
Please summarize the reason(s) why your agency is requesting a Corrective Action Plan.
_________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

## Slide 55: CORRECTIVE ACTION PLAN FORM HCBS REQUIREMENT
The setting is integrated in and supports full access of individuals receiving Medicaid HCBS to the greater community, including opportunities to seek employment and work in competitive integrated settings, engage in community life, and receive services in the community, to the same degree of access as individuals not receiving Medicaid HCBS at 42 CFR §441.301(c)(4)(i) (entire criterion except for “control personal resources”)
MILESTONE | BEGIN DATE | END DATE | NOTES
Notes: GOALS: POC SHOULD DOCUMENT:
PROVIDE OPPORTUNITIES TO SEEK INDIVIDUAL, COMPETITIVE EMPLOYMENT IN THE COMMUNITY- HOW WILL THIS BE DONE? GOALS?
ACTIVITIES ARE INTEGRATED IN THE COMMUNITY- INDIVIDUAL CHOICES AND HOW THEY ARE PROVIDED
CONTROLLING PERSONAL RESOURCES.. MAY BE A GOAL TO DO THIS

## Slide 56: CORRECTIVE ACTION PLAN FORM HCBS REQUIREMENT
The setting is selected by the individual from among setting options including non-disability specific settings and an option for a private unit in a residential setting. The setting options are identified and documented in the person-centered service plan and are based on the individual’s needs, preferences, and for residential settings, resources available for room and board at 42 CFR §441.301(c)(4)(ii),
MILESTONE | BEGIN DATE | END DATE | NOTES
Notes: GOAL: PERSON CENTERED POC AND ATTACHMENTS SHOULD DOCUMENT THE INDIVIDUAL’S NEEDS, PREFERENCES FOR THE SETTING THEY HAVE CHOSEN BUT THEN THE SETTING SHOULD DOCUMENT THE CHOICES PROVIDE TO THE INDIVDUAL AND HOW THIS IS DONE AND WHAT THE INDIVIDUAL CHOOSES TO DO

## Slide 57: CORRECTIVE ACTION PLAN FORM HCBS REQUIREMENT
Optimizes, but does not regiment, individual initiative, autonomy, and independence in making life choices, including but not limited to, daily activities, physical environment, and with whom to interact at 42 §CFR 441.301(c)(4)(iv).
MILESTONE | BEGIN DATE | END DATE | NOTES
Notes: POC SHOULD DOCUMENT THE CHOICES AND HOW THEY ARE GIVEN AND WHAT IS CHOSEN AND HOW WILL THE INDIVIDUAL BE SUPPORTED

## Slide 58: CORRECTIVE ACTION PLAN FORM HCBS REQUIREMENT
Facilitates individual choice regarding services and supports, and who provides them at 42 §CFR 441.301(c)(4)(v).
MILESTONE | BEGIN DATE | END DATE | NOTES

## Slide 59: CORRECTIVE ACTION PLAN FORM
The Corrective Action Plan for the provider agency, _____________________________________, was reviewed on ___________________.
Check the appropriate determination:
____________ CAP Approved
____________ CAP may be approved with modifications and follow up is required with provider
____________ CAP Disapproved and the disenrollment process will begin
COMMENTS ON CAP:
________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________
LGE/OCDD Representative: _______________________________________________ Date: _________________
Provider was notified of their results on: _____________________
Provider follow up for modifications occurred on: ____________________
Provider resubmitted CAP on: _____________________
Disenrollment will begin on: _____________________

## Slide 60: HCBS ONGOING COMPLIANCE

## Slide 61: Ongoing HCBS Settings Compliance: Overview
States are required to have mechanisms in place for ongoing monitoring, to detect areas of non-compliance and to ensure continued systemic compliance with the HCBS settings criteria.
LA described how ongoing monitoring will occur to ensure person centered planning is occurring, individual’s are able to provide feedback, and settings will remain in compliance and steps that will be taken to remediate any provider compliance issues. Some of these measures include:
  Annual survey, with every individual who is receiving waiver services, to ensure they are receiving the services they want and know their options
  In addition to the annual survey, an annual onsite visit with those individuals who reside in a provider owned/controlled setting, to ensure they are able to make choices regarding such things as food, visitors when they want, decorating, etc. and to ensure that a lease is in place to protect them.
  Annually, nonresidential providers will complete an onsite self-assessment as well as receive an onsite visit to ensure choice is being given, community integration is occurring and individuals are having employment opportunities and training is occurring with staff on the HCBS requirements and people first language.
  Annually, individuals who are of working age, will have a discussion on employment.
  Ongoing training for providers and SCs to ensure that the requirements for the HCBS Settings Rule are at the forefront, including PCP, employment etc.
Notes: HCBS WILL ALWAYS BE AROUND AND WE HAVE TO ENSURE THAT EVERYONE REMAINS COMPLIANT
WE REPORT TO CMS ON COMPLIANCE AT LEAST ANNUALLY

## Slide 62: WRAP UP

## Slide 63: SUMMARY
The HCBS Settings Rule ensures basic requirements for individuals receiving Medicaid HCBS.
LA will follow the CAP to bring the remaining settings into full compliance for requirements directly impacted by the PHE by 12/31/2024.
  LA will be working with providers who are not yet in compliance to move into compliance.
  Heightened scrutiny will be completed for those agencies that are HS.
Future Heightened Scrutiny obligations remain beyond the CAP period.
Ongoing monitoring is key to ensuring that settings remain compliant.
LA will continue to leverage stakeholders to strengthen our ongoing monitoring processes, and to ensure beneficiary complaint and feedback processes are followed.
Ongoing training is key to ensuring individuals, families, LGEs, providers, SCs, and stakeholders keep HCBS at the forefront.

## Slide 64: NEXT STEPS
June 1, 2023: ALL Nonresidential Providers will begin submitting the CAP Form and if necessary the CAP to the LGE. A CAP request will not be accepted after July 31, 2023. (*Providers please send CAP in ASAP, preferably by JUNE 30, 2023)
June 1, 2023: FINAL Validation visits for those providers who do not request a CAP on the CAP form will occur.
June 1, 2023- July 31, 2023: LGE/OCDD will review the CAP as they are received and notify the provider agency of the decision on the CAP.
June 1, 2023- January 31, 2024: If a CAP is requested and approved, the provider agency will work closely with the LGE/OCDD towards the milestones outlined in their CAP that will bring them into compliance.
July 31, 2023- January 30, 2024: Beginning July 31, 2023 and on the last day of the month thereafter, the Provider agency will provide updates to the CAP to the LGE.
February 1, 2024- July 31, 2024: Final Onsite Validation Visits will occur for those providers who were under a CAP.
June 1, 2023- January 30, 2024: Ongoing trainings will occur around the HCBS Settings rule and People First Language.

## Slide 65
Rosemary M. Morales, M.A.
OCDD STATE OFFICE
ROSEMARY.MORALES@LA.GOV
225-315-1239 (CELL)